## KPI & DORA Summary
AI-Code-Reviewer Enterprise — Engineering KPI & DORA Metrics Dashboard
Comprehensive audit report and quantitative performance tracking for Board Review (August 2026)
Metric Category | Indicator Name | Q1 Actual | Q2 Actual | Q3 Actual | Q4 Projection | Target / SLA | Status
DORA Metrics | Deployment Frequency (Deploys/Month) | 5 | 12 | 18 | 25 | >= 20 | On Track
DORA Metrics | Lead Time for Changes (Hours) | 12 | 8 | 4 | 2 | < 4.0 | Exceeding
DORA Metrics | Mean Time to Recovery (MTTR - Hrs) | 2.5 | 1.8 | 1 | 0.5 | < 1.0 | On Track
DORA Metrics | Change Failure Rate (%) | 4.5 | 3.2 | 2 | 1 | < 2.0 | On Track
Product Health | SAST Finding Accuracy (%) | 90 | 92 | 94 | 96 | >= 95.0 | Near Target
Product Health | AI Bug Prediction Precision (%) | 88 | 91 | 94 | 95.5 | >= 90.0 | Exceeding
Product Health | Dependency Graph Analysis Pass (%) | 95 | 96.5 | 98 | 99 | >= 98.0 | On Track
Product Health | Secret Scan False Positive Rate (%) | 3.5 | 2.1 | 1.2 | 0.5 | < 1.0 | Near Target
Team Scaling | Engineering Headcount (Actual) | 4 | 5 | 8 | 12 | 12 | Aligned
Team Scaling | Engineering Headcount (Target) | 4 | 6 | 10 | 14 | 14 | Review
Team Scaling | Retention Rate - AI/Core (%) | 100 | 100 | 95 | 95 | >= 90.0 | Exceeding
Phase 1 Execution | v1.1.0 Release Completion (%) | 0 | 0 | 100 | 100 | 100 | Completed
Phase 1 Execution | i18n Localization Foundation (%) | 0 | 0 | 100 | 100 | 100 | Completed
Phase 1 Execution | Security Audit & DPA Readiness (%) | 0 | 50 | 85 | 100 | 100 | In Progress
Phase 1 Execution | Design Partner Pilot Cohort (%) | 0 | 30 | 60 | 100 | 100 | In Progress